## Postman
MVC
General Analysis
Name | Status | Priority | Date | Time | Item ID
Sprint backlog |  | Urgent | 2020-01-01 | 1 | 400040239
General Analysis |  | Very High | 2020-01-01 | 1 | 400040241
Planing |  | Very High | 2020-01-01 | 1
List Task |  | Urgent | 2020-01-01 | 1 | 400196227
Estimate time |  | Medium | 2020-01-01 | 0.5 | 400250003
Set schedule |  | Medium | 2020-01-01 | 0.5 | 400250715
Daily Scrum |  | Medium | 2020-01-01 | 1 | 400428238
Project requirements |  | High | 2020-01-01 | 0.5 | 400237756
Define quality control managment |  | Medium | 2020-01-01 | 0.2 | 400240092
Define Risk and Incidents managment |  | Medium | 2020-01-01 | 0.2 | 400240507
Sprint review meeting |  | Low | 2020-01-01 | 1 | 400430180
Product Backlog |  | High | 2020-01-01 | 1 | 400430773
8.9
General Analysis
Name | Status | Priority | Date | Time | Item ID
Search Information |  | Low | 2019-12-11 | 1 | 400409215 | Very High
Ask the items |  | Low | 2019-12-12 | 2 | 401244108 | Medium
Draw the images |  | Low | 2019-12-12 | 1 | 400195273 | High
4
Planning
Name | Status | Priority | Date | Time | Item ID
Workflow Git | Done | Urgent | 2019-12-12 | 0.1 | 400255403 | Done
Structure Project Folder | Done | Very High | 2019-12-12 | 0.2 | 400388111 | Working on it
Software requirements | Ongoing | High | 2019-12-12 | 0.4 | 400410766 | Ongoing
0.7
Design
Name | Status | Priority | Date | Time | Item ID
Web Structure |  | Low | 2019-12-12 | 0.5 | 400391673
Wireframe |  | Low | 2019-12-12 | 0.2 | 400391854
0.7
Development
Name | Status | Priority | Date | Time | Item ID
Routes Structure |  | Very High | 2019-12-13 | 1 | 400474592
URL Cleans |  | Very High | 2019-12-12 | 3 | 401221343 |  | htaccess | llamar controladores y modelos | llamar mains MVC desde index
Main MVC |  | Urgent | 2019-12-13 | 2 | 400504661 |  | Heredar desde main la ruta error
DB Connections |  | Medium | 2019-12-13 | 1 | 401227412 |  | Conectar al servidor y base de datos
Entities |  | Very High | 2019-12-13 | 1.5 | 400501015 |  | crear objeto con propiedades tablas sql
Controllers |  | Low | 2019-12-14 | 1.5 | 400503264 |  | Heredar desde maincontroller |  |  | Lllamar vistas y modelos |  | obtener datos de modelos | lanzar datos a las vistas
Models |  | Medium | 2019-12-13 | 1 | 400493007 |  | crear metdos |  | querys mysql |  | obtener datos de tablas
Views |  | Low | 2019-12-15 | 1 | 400513630 |  | visualizar datos
9
Test
Name | Status | Priority | Date | Time | Item ID
LocalStorage test |  | Urgent | 2019-12-14 | 1 | 401237694
W3C Validation |  | Medium | 2019-12-14 | 0.1 | 400508705
Browsers |  | High | 2019-12-14 | 0.2 | 400511497
Mobiles |  | High | 2019-12-15 | 0.2 | 400511754
SEO |  | Small Low | 2019-12-15 | 0.1 | 400511816
Sprint review |  | Low | 2019-12-15 | 1 | 400513722
Fixed Troubles |  | High | 2019-12-15 | 1 | 401238559
3.6
Quality
Name | Status | Priority | Date | Time | Item ID
Test Metrics |  | Medium | 2019-12-16 | 0.3 | 400512170
Check parameters |  | Low | 2019-12-16 | 0.3 | 400512466
Sprint review |  | Small Low | 2019-12-16 | 1 | 400513783
1.6
Monitoring Control
Name | Status | Priority | Date | Time | Item ID
Create Readme |  | Medium | 2019-12-17 | 1 | 401237373
Redact document |  | High | 2019-12-17 | 3 | 401238956
4

## Postman_Pill
POSTMAN
Discovery
Name | Status | Priority | Date | Time | Item ID
Sprint backlog |  | Urgent | 2020-01-23 | 0.5 | 400040239
General Analysis |  | Very High | 2020-01-23 | 2 | 400040241
Planing |  | Very High | 2020-01-23 | 3.2
Daily Scrum |  | Medium | 2020-01-23 | 0.5 | 400428238
Project requirements |  | High | 2020-01-23 | 0.5 | 400237756
Define quality control managment |  | Medium | 2020-01-23 | 0.2 | 400240092
Define Risk and Incidents managment |  | Medium | 2020-01-23 | 0.2 | 400240507
Sprint review meeting |  | Low | 2020-01-23 | 1 | 400430180
Product Backlog |  | High | 2020-01-23 | 1 | 400430773
9.1
General Analysis
Name | Status | Priority | Date | Time | Item ID
Install Postman |  | Low | 2020-01-15 | 0.2 | 400409215 | Very High
Analyze the interface |  | Low | 2020-01-15 | 0.3 | 401244108 | Medium
Put it into practice |  | Low | 2020-01-15 | 0.5 | 400195273 | High
Search Information |  | Low | 2020-01-15 | 1
2
Planning
Name | Status | Priority | Date | Time | Item ID
Pill organization |  | Urgent | 2020-01-16 | 0.7 | 400196227
List Task |  | Urgent | 2020-01-16 | 1 | 400196227
Estimate time |  | Medium | 2020-01-16 | 0.5 | 400250003
Workflow Git | Done | Urgent | 2020-01-17 | 0.1 | 400255403 | Done
Structure Project Folder | Done | Very High | 2020-01-17 | 0.2 | 400388111 | Working on it
Software requirements | Ongoing | High | 2020-01-17 | 0.4 | 400410766 | Ongoing
Tools used. | Ongoing | High | 2020-01-17 | 0.3
3.2
Development
Name | Status | Priority | Date | Time | Item ID
New collection |  | Very High | 2020-01-17 | 1 | 400474592
Testings |  | Very High | 2020-01-17 | 3 | 401221343 |  | htaccess | llamar controladores y modelos | llamar mains MVC desde index
Monitor |  | Very High | 2020-01-17 | 2 | 400504661 |  | Heredar desde main la ruta error
Document API |  | Medium | 2020-01-17 | 1 | 401227412 |  | Conectar al servidor y base de datos
Export Collection |  | Very High | 2020-01-17 | 1.5 | 400501015 |  | crear objeto con propiedades tablas sql
|  | Urgent | 2020-01-17 |  | 400503264 |  | Heredar desde maincontroller |  |  | Lllamar vistas y modelos | obtener datos de modelos | lanzar datos a las vistas
7
Monitoring Control
Name | Status | Priority | Date | Time | Item ID
Check requirements acomplished |  | Medium | 2020-01-17 | 1 | 401237373
Redact document |  | High | 2020-01-17 | 3 | 401238956
Check deliverables |  | Medium | 2020-01-17 | 1
5
21.1

## Postman_Pill Tasks
POSTMAN
Name | Status | Priority | Date | Time | Item ID
Discovery |  |  |  | 9.1
Sprint backlog |  | Urgent | 2020-01-23 | 0.5 | 400040239
General Analysis |  | Very High | 2020-01-23 | 2 | 400040241
Planing |  | Very High | 2020-01-23 | 3.2
Daily Scrum |  | Medium | 2020-01-23 | 0.5 | 400428238
Project requirements |  | High | 2020-01-23 | 0.5 | 400237756
Define quality control managment |  | Medium | 2020-01-23 | 0.2 | 400240092
Define Risk and Incidents managment |  | Medium | 2020-01-23 | 0.2 | 400240507
Sprint review meeting |  | Low | 2020-01-23 | 1 | 400430180
Product Backlog |  | High | 2020-01-23 | 1 | 400430773
9.1
General Analysis |  |  |  | 2
Name | Status | Priority | Date | Time | Item ID
Install Postman |  | Low | 2020-01-23 | 0.2 | 400409215 | Very High
Analyze the interface |  | Low | 2020-01-23 | 0.3 | 401244108 | Medium
Put it into practice |  | Low | 2020-01-23 | 0.5 | 400195273 | High
Search Information |  | Low | 2020-01-23 | 1
2
Planning |  |  |  | 3.2
Name | Status | Priority | Date | Time | Item ID
Pill organization |  | Urgent | 2020-01-23 | 0.7 | 400196227
List Task |  | Urgent | 2020-01-23 | 1 | 400196227
Estimate time |  | Medium | 2020-01-23 | 0.5 | 400250003
Workflow Git | Done | Urgent | 2020-01-23 | 0.1 | 400255403 | Done
Structure Project Folder | Done | Very High | 2020-01-23 | 0.2 | 400388111 | Working on it
Software requirements | Ongoing | High | 2020-01-23 | 0.4 | 400410766 | Ongoing
Tools used. | Ongoing | High | 2020-01-23 | 0.3
3.2
Development |  |  |  | 7
Name | Status | Priority | Date | Time | Item ID
New collection |  | Very High | 2020-01-24 | 1 | 400474592
Testings |  | Very High | 2020-01-24 | 3 | 401221343 |  | htaccess | llamar controladores y modelos | llamar mains MVC desde index
Monitor |  | Very High | 2020-01-24 | 2 | 400504661 |  | Heredar desde main la ruta error
Document API |  | Medium | 2020-01-24 | 1 | 401227412 |  | Conectar al servidor y base de datos
Export Collection |  | Very High | 2020-01-24 | 1.5 | 400501015 |  | crear objeto con propiedades tablas sql
|  | Urgent | 2020-01-17 |  | 400503264 |  | Heredar desde maincontroller |  |  | Lllamar vistas y modelos | obtener datos de modelos | lanzar datos a las vistas
7
Monitoring Control |  |  |  | 5
Name | Status | Priority | Date | Time | Item ID
Check requirements acomplished |  | Medium | 2020-01-24 | 1 | 401237373
Redact document |  | High | 2020-01-24 | 3 | 401238956
Check deliverables |  | Medium | 2020-01-24 | 1
5
Total |  |  |  | 21.1

## Sprints
POSTMAN
Name | Status | Priority | Date | Time | Item ID
Discovery |  |  |  | 9.1
Sprint backlog |  | Urgent | 2020-01-23 | 0.5 | 400040239
General Analysis |  | Very High | 2020-01-23 | 2 | 400040241
Planing |  | Very High | 2020-01-23 | 3.2
Daily Scrum |  | Medium | 2020-01-23 | 0.5 | 400428238
Project requirements |  | High | 2020-01-23 | 0.5 | 400237756
Define quality control managment |  | Medium | 2020-01-23 | 0.2 | 400240092
Define Risk and Incidents managment |  | Medium | 2020-01-23 | 0.2 | 400240507
Sprint review meeting |  | Low | 2020-01-23 | 1 | 400430180
Product Backlog |  | High | 2020-01-23 | 1 | 400430773
9.1
| General Analysis |  |  | 2
| Name | Priority | Date | Time | Item ID
| Install Postman | Low | 2020-01-23 | 0.2 | 400409215 | Very High
| Analyze the interface | Low | 2020-01-23 | 0.3 | 401244108 | Medium
| Put it into practice | Low | 2020-01-23 | 0.5 | 400195273 | High
| Search Information | Low | 2020-01-23 | 1
2
| Planning |  |  | 3.2
Name | Status | Priority | Date | Time | Item ID
Pill organization |  | Urgent | 2020-01-23 | 0.7 | 400196227
List Task |  | Urgent | 2020-01-23 | 1 | 400196227
Estimate time |  | Medium | 2020-01-23 | 0.5 | 400250003
Workflow Git | Done | Urgent | 2020-01-23 | 0.1 | 400255403 | Done
Structure Project Folder | Done | Very High | 2020-01-23 | 0.2 | 400388111 | Working on it
Software requirements | Ongoing | High | 2020-01-23 | 0.4 | 400410766 | Ongoing
Tools used. | Ongoing | High | 2020-01-23 | 0.3
3.2
Development |  |  |  | 7
Name | Status | Priority | Date | Time | Item ID
New collection |  | Very High | 2020-01-24 | 1 | 400474592
Testings |  | Very High | 2020-01-24 | 3 | 401221343 |  | htaccess | llamar controladores y modelos | llamar mains MVC desde index
Monitor |  | Very High | 2020-01-24 | 2 | 400504661 |  | Heredar desde main la ruta error
Document API |  | Medium | 2020-01-24 | 1 | 401227412 |  | Conectar al servidor y base de datos
Export Collection |  | Very High | 2020-01-24 | 1.5 | 400501015 |  | crear objeto con propiedades tablas sql
|  | Urgent | 2020-01-17 |  | 400503264 |  | Heredar desde maincontroller |  |  | Lllamar vistas y modelos | obtener datos de modelos | lanzar datos a las vistas
7
Monitoring Control |  |  |  | 5
Name | Status | Priority | Date | Time | Item ID
Check requirements acomplished |  | Medium | 2020-01-24 | 1 | 401237373
Redact document |  | High | 2020-01-24 | 3 | 401238956
Check deliverables |  | Medium | 2020-01-24 | 1
5
Total |  |  |  | 21.1

## Algorithms
| TASKS | SUBTASKS 1 | SUBTASKS 2 | SUBTASKS 3
TASK 1 | New collection | Name
|  | methods | GET | Headers, key
|  | Network Chrome | POST | Body, keys
|  | Select an authorization type | JSON
Enter a pre-request script to execute before the collection runs.
TASK 2 | Testings | Test result | Code scritps | state code
code is (OK, Created, ...)
The answer has body
The answer is in JSON
The header has “Content-Type”
The response time is less than 200ms
TASK 3 | Monitor | Monitor | Set up
TASK 4 | Document API
Export Collection

## Checkings
CHECK REQUIREMENTS ACOMPLISHED
| N° | REQUIREMENT | CHECK
| 1 | Create a clear and orderly directory structure | OK | Create a clear and orderly directory structure
| 2 | Both the code and the comments must be written in English | OK | Both the code and the comments must be written in English
| 3 | Use the camelCase code style to define variables and functions | OK | Use the camelCase code style to define variables and functions
| 4 | In the case of using HTML, never use online styles | OK | In the case of using HTML, never use online styles
| 5 | In the case of using different programming languages ​​always define the implementation in separate terms | OK | In the case of using different programming languages ​​always define the implementation in separate terms
| 6 | Remember that it is important to divide the tasks into several sub-tasks so that in this way you can associate each particular step of the construction with a specific commit | OK | Remember that it is important to divide the tasks into several sub-tasks so that in this way you can associate each particular step of the construction with a specific commit
| 7 | You should try as much as possible that the commits and the planned tasks are the same |  | You should try as much as possible that the commits and the planned tasks are the same
| 8 | Delete files that are not used or are not necessary to evaluate the project | OK | Delete files that are not used or are not necessary to evaluate the project
CHECK DELIVERABLES
| N° | DELIVERABLE | CHECK
| 1 | Repository with all project files | OK | Repository with all project files
| 2 | You must create a correctly documented README file in the root directory of the project (see guidelines in Resources) | OK | You must create a correctly documented README file in the root directory of the project (see guidelines in Resources)
| 3 | Documentation of the pill in PDF format |  | Documentation of the pill in PDF format
| 4 | Presentation of the pill in PDF format |  | Presentation of the pill in PDF format
| 5 | POSTMAN collection into the project repository |  | POSTMAN collection into the project repository